KORA

Implementation Plan & Feature Ticket List

Sprint Plan, Task Breakdown, and Engineering Tickets

| Document Type | Implementation Plan + Feature Tickets |
| --- | --- |
| Version | v1.0 |
| Date | June 2026 |
| Status | ACTIVE — v1.0 Release Target |

# 1. Implementation Philosophy

Build thin end-to-end slices, not thick horizontal layers. Every sprint ships something a student can use. The order of implementation is determined by dependency graph, not by perceived difficulty or completeness.

Golden Rule Before writing any feature code, one student must be waiting to use it. Ship to beta users at the end of every sprint. If no student is asking for the next feature, you are building the wrong thing.

# 2. Project Setup Checklist

## Monorepo Structure

- kora/ (root)

  - apps/mobile — Expo React Native app

  - apps/backend — FastAPI Python service

  - apps/wa-bridge — Node.js Baileys WhatsApp bridge

  - packages/shared — shared TypeScript types, constants

  - infra/ — Docker Compose, deployment configs

## Day 1 Setup Tasks

- Install: Python 3.11, Node 20, Ollama, Redis, Neo4j Desktop

- Pull: ollama pull llama3.2-vision

- Docker Compose: Redis + Neo4j + PostgreSQL

- Create FastAPI skeleton with /health endpoint

- Create Expo app with Expo Router

- Wire phone app to FastAPI via local IP — verify round trip

# 3. Sprint Plan

## Sprint 0 — Hackathon (3 days)

| # | Ticket | Owner | Acceptance Criteria |
| --- | --- | --- | --- |
| S0-1 | FastAPI bridge skeleton | Backend | POST /chat returns hello. Phone can call it. |
| S0-2 | Expo app shell | Mobile | App opens, shows chat input, connects to backend |
| S0-3 | Image capture → base64 | Mobile | Camera opens, image encoded, sent to /ingest/image |
| S0-4 | Gemini Vision OCR | Backend | Image input returns structured text in < 4s |
| S0-5 | Schedule parse agent | Backend | OCR text → JSON: [{day, time, subject, room}] |
| S0-6 | SQLite persistence | Backend | Schedule events saved, returned on GET /schedule |
| S0-7 | Chat response display | Mobile | Agent text response shown in chat bubbles |
| S0-8 | Demo script | All | Live demo: phone photo → schedule confirmed in chat |

## Sprint 1 — Core Agents (Week 1–2)

| # | Ticket | Owner | Acceptance Criteria |
| --- | --- | --- | --- |
| S1-1 | LangGraph orchestrator | Backend | Intent classified correctly for 5 agent types, 90% accuracy on test set |
| S1-2 | Deadline agent | Backend | WhatsApp text → deadline entity with due_date extracted |
| S1-3 | Expense agent + OCR | Backend | Receipt photo → amount + merchant + category in < 5s |
| S1-4 | Study agent | Backend | PDF upload → 10 flashcards generated in < 30s |
| S1-5 | mem0 integration | Backend | Agent remembers user's college, branch across sessions |
| S1-6 | ChromaDB notes store | Backend | Note text chunked, embedded, searchable by query |
| S1-7 | Neo4j knowledge graph | Backend | Student → Subject → Exam relationships queryable |
| S1-8 | Voice input (Whisper) | Mobile/BE | 10s voice clip → text intent in < 2s |
| S1-9 | Baileys WA bridge | Backend | WA messages forwarded to /whatsapp/webhook |
| S1-10 | Schedule screen UI | Mobile | Weekly timetable rendered from API data |

## Sprint 2 — Polish + Proactive (Week 3–4)

| # | Ticket | Owner | Acceptance Criteria |
| --- | --- | --- | --- |
| S2-1 | Celery proactive loop | Backend | Deadline nudge sent 24h before due date via push |
| S2-2 | Push notifications | Mobile/BE | FCM integration, foreground + background delivery |
| S2-3 | Deadlines screen UI | Mobile | Sorted by urgency, swipe to complete, colour banding |
| S2-4 | Expenses screen UI | Mobile | Monthly summary, transaction feed, camera FAB |
| S2-5 | Onboarding flow | Mobile | 7-step onboarding, college picker, first timetable scan |
| S2-6 | Auth (OTP + JWT) | Backend | Phone OTP → JWT issued, refresh token rotation |
| S2-7 | Error states + loading | Mobile | Skeleton loaders, retry on error, offline banner |
| S2-8 | PostHog analytics | Backend | Key events tracked: session_start, deadline_created, expense_logged |
| S2-9 | Beta APK build | Mobile | Expo EAS build, distributed to 10 beta users |
| S2-10 | Content agent (basic) | Backend | Draft leave email from context in < 10s |

# 4. Definition of Done

A ticket is DONE only when all of the following are true:

- Feature works on a real Android device (not just emulator)

- API endpoint has passing unit tests (pytest, > 80% coverage for new code)

- No console errors or warnings in React Native

- PostHog event fires correctly for the user action

- One beta user has confirmed the feature works for their actual use case

# 5. Tech Debt Backlog (Known, Deferred)

| Item | Priority | Notes |
| --- | --- | --- |
| SQLite → PostgreSQL migration | P1 | Do before 100 users |
| iOS app (Expo build) | P1 | Android first, iOS in parallel from Sprint 2 |
| Rate limiting on all endpoints | P0 | Redis bucket — add in Sprint 1 |
| End-to-end encryption for WA bridge | P1 | After launch, before 1000 users |
| CGPA projection engine | P2 | v1.1 feature |
| Multi-language OCR (Hindi-heavy) | P1 | Fine-tune PaddleOCR on IIT/NIT timetables |
| Offline mode | P2 | Cache last-known state, queue sync on reconnect |

# 6. Launch Checklist

## Pre-Beta

- Load test: 50 concurrent users, FastAPI handles without degradation

- Security review: OWASP Top 10 scan on all endpoints

- Privacy audit: confirm no PII logged in application logs

- DPDP consent flow: privacy policy + consent screen before WhatsApp connect

## Beta Launch

- 50 students, 1 college, in-person onboarding session

- Daily Discord/WhatsApp group for bug reports

- Weekly metrics review: D7 retention, tasks per user, error rate

- Personal follow-ups with every churned user in week 1

## YC Application Milestone

- D30 retention > 40% demonstrated

- Weekly active users: > 50 with > 5 tasks/week

- One quantified student success story (deadline saved, grade improved)

- YC W26 application submitted with metrics and working demo link